EDCMM 992.6 PROJECT PROPOSAL

out your front door: a youth-led community development experience

A front-end analysis

Submitted to Dr. Richard Schwier

Submitted by Jordan Epp

Student #10015102

November 15, 2008

Table of Contents

Introduction and Context ................................................... p3

Note ............................................................................. p4

Project .......................................................................... p5

Product ......................................................................... p5

Literature Review ............................................................ p6

Methodology .................................................................. p8

Timeline ........................................................................ p10

References .................................................................... p11

Literature Review Articles ................................................. p11

Appendices

Out Your Front Door Sample Timeline ................................. p13

Out Your Front Door Project Stages ................................... p14

EDCMM 992.6 PROJECT PROPOSAL

out your front door: a youth-led community development experience

A front-end analysis

Title

Out Your Front Door (OYFD)

Introduction and Context

Educators know there are innumerable factors that affect a students ability to learn. Schools geographically located in neighbourhoods with lower than average incomes consistently report low attendance records and high drop out rates. Further issues are reflected in respect issues causing vandalism, self deprecation, and low self worth. These issues seem to stem from the socio-political and socio-economic problems faced by many youth within the core neighbourhood's public school system. The cold facts are that social realities of drug and alcohol abuse, factors dealing with nutrition and health, local gang activity and prostitution, compounded by the daily pressures of adolescence all contribute to these attendance and drop-out numbers. The larger picture reveals that for core neighbourhoods, the social realities often trump the educational needs. Students have difficulty engaging in classroom activities when there are greater issues with more immediate consequence on their minds. Therefore a change in instructional delivery and content seems necessary to re-engage students while directly facing the social issues that cause the disruptions.

In 2007 Maclean's magazine published an article entitled Canada's Worst Neighbourhood. The article's sights was aimed squarely at the community of North Central Regina. Some of the claims MacLean's made were that North Central was, “among the poorest spots in urban Canada”, “A typical child will attend all four of the neighbourhood's elementary schools in the course of a single academic year.”, and “Now it's dirt-poor and dangerous.” (Gatehouse, 2007). The community of North Central took the article very personally. Many saw a different side to their neighbourhood, one that Gatehouse had overlooked or ignored.

In 2008 Scott Collegiate, located in the heart of North Central Regina, voiced their rebuttal to MacLean's article and prepared, produced and performed a dinner theatre cleverly entitled Eat Your Words. This production not only showcased the talents of the Drama 10 class but that of the English A10/B10, Commercial Cooking 10, Information Processing 10, and Tourism, Hospitality and Entrepreneurship 10 students as well. This collaborative effort allowed students to voice their opinions, gain credits in all subjects where they were involved, and most importantly, it engaged them in learning through an alternative delivery of content. I was able to play a small role during this production as part of my work at Educational Media Access & Production on the University of Saskatchewan campus. As part of a documentary series on evolving education we covered the event and were able to gather feedback and comments on the success of the evening and the problem-based learning program as a whole.

Note

It is important when reading this proposal to distinguish between project and product. The product that will be submitted for 992 is that of a complete front-end analysis. The project is a multi-stage engagement with students in a secondary school setting. This project will not be implemented as part of the 992 course requirements. It will, however, be referenced throughout this proposal. The front-end analysis of this project will be submitted as the product of 992's course requirements.

Project

Out Your Front Door (OYFD) is a community development project that will be designed to engage youth in local leadership and community building while developing online networking skills through situated learning models. Using an asset-based community approach, youth will design and  lead an asset-mapping research project. Collecting data such as surveys, photographs, interviews, and statistics, relevant to their local community the resulting study will be transformed into a living 3D model of their neighbourhood within the online virtual world of Second Life (SL). Once in Second Life students will have the opportunity to create their own avatar, learn 3D modelling techniques, design and build objects using SL primitives, and learn basic action scripting within SL. From this virtual model of their neighbourhood students will assess their communities assets and liabilities and develop strategies for community building within the physical streets and avenues of their community.  Aside from bi-weekly face-to-face sessions, and online social networking tools, students will keep track of their progress by developing and managing a wiki in which to display and follow advances in the building process and asset mapping progress.

Product

This proposal outlines a project for which a complete front-end analysis will be produced. By March 2009 a thorough needs assessment will be completed. This analysis will follow the Instructional Design protocol for needs assessment and deliver a packaged analysis of the intended learners, further investigation into the context of the program, and a task/content analysis for each of the three stages of the project. This packaged front-end analysis will provide the necessary information to complete a project design including recommendations for applications and tools, timelines, and resources. Although this complete project design will not be included in the March 992.6 submission, the complete needs assessment that will be delivered will provide the information necessary for prototype development. The targeted audience for this analysis are those instructors who will develop and carry out the final program.

Literature Review

Development

There are two main focuses for researching literature related to development. As the project combines community development with youth development our research into both will be important. Camino (2005) draws attention to the lack of literature looking at the best practices for youth-led community building. There are a wealth of articles looking at community development best practices as well as best practices relating to youth development, but there is little research done into the combination of the two and the effects on the youth and communities involved. Therefore the research will combine articles looking at community building and youth development best practices separately.

A few articles combining youth development with community building that have been found will also be included in the review. Both Camino (2005) and Nitzberg (2005) attempt to begin the investigation into the best practices for youth-based community development. Nitzberg is a senior faculty member at the Cambridge College where they have been developing courses linking academia and the processes of the community, thus strengthening the town and gown relationship.  Nitzberg (2005) lists several academic's understanding of best practices in the field's of community development and youth development. These lists are then reviewed by Nitzberg as he outlines five goals for the meshing of these practices. Camino (2005), a senior scientist at the University of Wisconsin-Madison, looks at the question, “What practices proved promising in enabling the service-learners to engage their voices, and lead youth and adults in community building?” (Camino, 2005). Camino reviews several research studies to answer this question and found three major results that will be utilized in OYFD.

Virtual Communities and Social Networking

The third element the literature review will reflect is the effect of virtual environments on learning. Specifically, the interest for this project is in situated learning. One article deserving specific mention is a recent article by Ondrejka (2008). Ondrejka examines the impact of Second Life (SL) on education. After a brief history of virtual worlds, Ondrejka goes on to describe the nature of interaction in Second Life and it's relationship to situated learning among other models. This article stops short of describing best practices, but delivers a clear understanding of how virtual environments such as Second Life foster self paced learning in young people. This research shows that the use of virtual environments like Second Life naturally encourage legitimate peripheral participation and situated learning (Ondrejka, 2008).

This social networking component of the project is designed to encourage peer to peer support and will help to develop a situation of learning trajectory, a form of Legitimate Peripheral Participation, where students move through Wenger's (1998) five types of learning trajectories. Using these learning models compliments the assets for positive youth development described by Camino (2005). Students become engaged and begin moving through learning trajectories becoming more engaged as they develop leadership skills (Wenger, 1998).

Socio-political effects

Information regarding socio-political dynamics of the intended user groups as well as the environmental context must be studied. It is important for both the learner analysis and the context analysis to have information gathered about the effects of socio-political dynamics on youth. Part of this research will review case studies I have been involved in personally. The first being the above mentioned dinner theatre put on by Scott Collegiate in 2008. This successful program provides excellent information about youth engagement and effective models of instruction in an environment of poorer socio-economic climates. The second case study is a program called YouthDOCS. YouthDOCS ran as a pilot project funded by the Saskatchewan Youth Project Awards in the Summer of 2006. Stationed at the White Buffalo Youth Lodge in Saskatoon’s West end, YouthDOCS took three young filmmakers through the process of documentary filmmaking. Learning cinematography, audio recording, interviewing techniques, and post production, these youth completed there own documentaries and made the program a major success. In 2007 YouthDOCS teamed up with PAVED Arts and Saskatchewan Governments Community Initiatives Grant to provide an additional four programs throughout the year. This program had many of the same leadership and engagement goals as OYFD and will be a major asset to the literature review.

Methodology

Following the instructional design protocol for needs assessment this product will break into several sections of analysis. Beginning with a needs assessment I will investigate the instructional need for this project and after identifying the problems I will explore how these needs can be addressed through instruction. This assessment will analyse the wants and needs of both the school and the students by referring to the case studies mentioned above. Reviewing the wants and needs addressed in these programs should provide a substantial list that will help identify potential conflicts during the project design phase outside the scope of this product. This needs assessment will create a defined focus for the rest of the analysis' where all other assessments will come back to the needs identified here.

Once the needs and wants of the program are identified I will begin a detailed context and learner analysis. These stages will be tightly connected as many of the contextual factors shaping the projects design also shape the learner characteristics of the target audience. Through review of literature and referencing the case studies mentioned above, I intend to compile these critical analysis'. Many of the learner characteristics displayed in the case studies mentioned above will be reflected in the learners targeted in OYFD. Context characteristics specific to community development, youth development, and online social networks will be revealed through an in-depth review of the literature.

As you will see in the timeline provided below, an extra week has been provided for the content/task analysis section of the assessment due to the large amount work required here. There are three major modules or stages that make up the content and structure of OYFD. Each of these modules presents its own challenges in terms of content/task analysis. A more descriptive explanation of the OYFD's stages is provided as an appendix to this document (Appendix 2). Referencing this appendix may add some clarity to the discussion of the front-end analysis. Learning outcomes and prerequisite analysis' will be important elements of all three stages. The first stage deals with community development and how it relates to youth and youth-at-risk.  This stage relies on many of the best practices outlined in the literature review. These practices will be put into action by the students, but must be modified based on a prerequisite analysis. Learner outcomes will be defined for this stage based on the best practices principles used in community development models.

The second stage of content is the online community built to deliver this project. A major use of online tools will be employed to deliver this project. Again, a prerequisite analysis will be critical to designing these online components. Information gathered from both case studies will provide information about prerequisite knowledge of this kind. Of course the learners characteristics will vary in terms of their specific prior learning and the design of the program will encourage legitimate peripheral participation and situated learning models. Ondrejka (2008) discusses remarkable learning curves being overcome through situated learning in virtual communities. The tasks of this module will not rely solely on peer-to-peer interaction, but will include intensive face-to-face sessions of technical training with instructors as well. This second stage encompasses a large part of the tasks required by the students. Therefore stage two, the online components of OYFD, have been given the largest amount of time for completion during the delivery of the project as seen in the sample project timeline provided (Appendix 1).

The third stage of OYFD involves bringing the project back to the physical world. Having built a 3D model of their neighbourhood based on the community asset-mapping skills they have developed, students will be asked to develop a strategy for change within their physical community and present their findings to the community. Within the front-end analysis being proposed here, I will at this stage set up objectives for the learning goals and determine the evaluation for these goals. These evaluations of objectives will later be used in the design prototype during this third stage of OYFD. Students will demonstrate their knowledge and completion of objectives through their presentation allowing their success to be evaluated based on the objectives and evaluations determined in this front-end analysis.

Timeline

| Date | Completed Element |
| --- | --- |
| November 15, 2008 | Submit Project Proposal |
| November 24, 2008 | Literature Review |
| December 15, 2008 | Needs Assessment |
| January 05, 2009 | Learner Analysis |
| January 26, 2009 | Context Analysis |
| February 23, 2009 | Content/Task Analysis |
| March 09, 2009 | Refine and Package, Project Report |
| March 14, 2009 | Submit front-end analysis and project report for OYFD |

References

Camino, L. (2005). Youth-Led Community Building: Promising Practices from Two Communities 	Using Community-Based Service-Learning. Journal of Extension, 43, (1), 1FEA2.

Gatehouse, J. (2007, January). Canada's worst neighbourhood. Maclean's. Retrieved November 10, 	2008, from http://www.macleans.ca/article.jsp?content=20070115_139375_139375

Nitzberg, J. (2005). The meshing of youth development and community building. New Directions for 	Youth Development, 106, 7-16.

Ondrejka, C. Education Unleashed: Participatory Culture, Education, and Innovation in Second 	Life. The Ecology of Games: Connecting Youth, Games, and Learning. Edited by K. Salen. 	The John D. and Catherine T. MacArthur Foundation Series on Digital Media and Learning. 	Cambridge, MA: The MIT Press, 2008. 229–252. doi: 10.1162/dmal.9780262693646.229

Wenger, E. (1998). Communities of Practice: Learning, meaning, and identity. New York: Cambridge 	University Press.

Literature Review Articles

Camino, L. (2005). Youth-Led Community Building: Promising Practices from Two Communities 	Using Community-Based Service-Learning. Journal of Extension, 43,(1), 1FEA2.

Driscoll, M.P. (2000). Psychology of Learning for Instruction second edition. Massachusetts, U.S.: 	Allyn & Bacon.

HeartWood Centre for Community Youth Development. (2004). A Framework for Community Youth 	Development. Halifax, NS: Can.

Hughes, K.L., & Wang Golann, J. (2008). A Virtual World with Real Results. Techniques, 34-38.

Nitzberg, J. (2005). The meshing of youth development and community building. New Directions for 	Youth Development, 106, 7-16.

Ondrejka, C. Education Unleashed: Participatory Culture, Education, and Innovation in Second 	Life. The Ecology of Games: Connecting Youth, Games, and Learning. Edited by K. Salen. 	The John D. and Catherine T. MacArthur Foundation Series on Digital Media and Learning. 	Cambridge, MA: The MIT Press, 2008. 229–252. doi: 10.1162/dmal.9780262693646.229

Southern Rural Development Center. (2002). Mapping Assets of Youth Community: A Key Component 	for Building Local Capacity. Mississippi, MS: Beaulieu, Lionel J.

The Joan Ganz Cooney Center at Sesame Workshop. (2007). D is for Digital: An Analysis of the 	Children's Interactive Media Environment With a Focus on Mass Marketed Products that 	Promote Learning. New York, NY: U.S.

Wenger, E. (1998). Communities of Practice: Learning, meaning, and identity. New York: Cambridge 	University Press.

Appendix 1

Out Your Front Door Sample Timeline

Appendix 2

Out Your Front Door Project Stages

Stage One:Community Development

One of the first activities the students will participate in is a pre-test to determine the students knowledge about what community development is, how they might get involved, the assets within their own community, and the level of participation they have shown in the past. This pre-test will not only aid in the evaluation of the program, but will also help to shape the content and identify local leaders within the group. Assessing the knowledge  base will guide our first steps in asset-mapping and show us where to begin.

Developing a wiki and learning to make entries and posts will be an important first stage development. Students will use the wiki as a bulletin board throughout the project. Similar to a community board at the corner store this wiki will share progress reports on the asset-mapping, and SL building progresses as the project moves along. The discussion board will be used to voice concerns, share incites, and ask questions of each other as they aid in one another's learning. If a student is unclear as to what to do next they can check the wiki. Sections for “to do” lists, completed tasks, updates, discussions, and questions will all be a part of the wiki's purpose. This wiki will be managed, and developed by the students and will be moderated by teachers and project leaders.

Learning best practices for community development and in particular asset-mapping will be the major task in stage one. Readings will be read and discussed in group sections during the first face-to-face session. After learning a few best practices and developing a general understanding of what makes a community asset, students will begin mapping their own neighbourhood for assets. Students will be asked to place markers on a map of their neighbourhood identifying commercial, institutional, and personal assets within their own community. Once a good level of assets has been established students will begin to develop their own strategies for filling in gaps within their asset-map. Surveys, statistics, and canvassing will all be used during this stage to map the remaining assets within the community. Students will be tasked with researching statistics online, canvassing the neighbourhood with surveys, and collecting data any way they see fit in order to create a full understanding of their community assets. Once these assets are well under way to being collected, youth will be introduced to Second Life.

Second Life (SL) has established two main grids of virtual space. The main grid and the teen grid. Procurement of land within the teen grid will allow us security while exploring the virtual world. Adults are not allowed on teen grid and second life employees or avatars with last name of Linden, police the grid for infiltrators. The only exception to the adult free rule is in the case of education. Educational islands may be purchased where an educator may be granted access to that island and that island only. They may not leave the island and warnings to other youth as they approach the island tells of an adult presence within this virtual space. Students, however, are free to leave the island and explore the teen grid and develop skills about beyond those offered on OYFD island. SL introduces users to avatars and virtual environments through what is called welcome island. This space leads new arrivals through a series of explorational learning modules that teach users how to change appearance, to sit, stand, touch objects, interact with objects, interact with one another, build crude elements, and even to fly. Students will be left, for the most part, to explore SL on this day with their activities moderated by teacher and project facilitators as real world tech support. This exploration through situated learning is excellent training for the collaborative efforts these youth will be required to practice throughout the project. Seeing and interacting both “in world” and in the physical world will ease students into the possibilities of communicating and collaborating through SL.

Stage Two: Building the Map

In stage two of OYFD, students will be using Second Life to build a 3D model of their community and attaching assets to the structures created. This process will create a living breathing model of the community they live in and develop an visual overview of their communities assets and liabilities. Literally viewable from any angle, students will have the opportunity to walk the streets, enter buildings, and fly above the neighbourhood for a bird's eye view, giving them a fuller picture of their communities make-up.

Learning to build 3D models in second life is a large task. Although SL includes all the tools for building there is a steep learning curve to overcome. Some students will take to this activity better than others. It is here that situated learning will be a major advantage. In the first face-to-face session of this stage, students will get hands on training from real world instructors on how to build basic shapes and create complex objects with them. Leaders among the youth will be identified at this stage and asked to become mentors for other students still struggling with this technical process. Further training can be attained through in world sessions which take place daily throughout SL. Students who do not find interest or pleasure in this technical process can be asked with other duties of the production. It is more important that the student feels useful and that their efforts are worthwhile than for them to participate equally in every task.

Although a high level of competency is expected from the group, creating an entire neighbourhood is a major construction task. A building team will be established by the group with for-mans and construction workers. Tasks will be divided up according to skill level. Although a large sample population is expected for this project, it must be understood that building an entire neighbourhood is a major construction project. Buildings, streets, landscaping, furniture, fixtures, textures, cars, bikes, fences, lamp posts, and more all need to be created in order to create a recognizable representation of the neighbourhood. To aid in the building process a pre-established model of the paved streets will be built prior to the students arrival within Second Life. This model will act as a blank canvas on which the students must create buildings to represent their community assets. 	Building will take place in phases in order to organize and manage time restraints. Assets collected during stage one will be broken into categories. The first phase of construction (2b, 2c on Appendix 1) will be to create building facades. Building the shell of a structure that represents one asset within the community will be important to making the streets look recognizable. Placing these assets within the virtual grid of streets will follow the address of the physical structure within their community. Spaces where assets have not been identified will be filled with a generic model of either a home, business, or other in order to save time and energy. The next phase of construction will be to create interiors for the asset buildings as well as exterior dressings including trees, street lights, cars, etc. This phase will require a great deal of time and organization. Five face-to-face sessions over thirteen weeks are set aside of the building and asset-mapping phases of stage two. At the end of construction the youth will have the opportunity to now walk the virtual streets of their community having observed and built every square inch of their neighbourhood. As stage two comes to an end students are reminded to reflect on the assets they have mapped and to now turn their attentions to assessing the community as a whole.

Stage Three: Bringing it Home

Stage three of the project tests the students new found levels of engagement. It is here that youth have the opportunity to assess there environment, both virtual and physical and critique what they now see. Putting all the tools and lessons they have acquired throughout the past year, students now turn a critical eye to their project and begin to devise strategies for community building initiatives. Asset-mapping does nothing if not followed up with a strong action plan. Following best practices outlined in our literature reviews, youth will develop strategies for bettering their neighbourhood. After assessing what the community has to offer it is important to plan new initiatives that compliment these existing amenities. Ideally community building means choosing actions that strengthen the communities existing assets, creating new networks of community members, business people and residents.

Youth will review their model looking for holes or gaps in the communities strengths. These gaps may include the lack of a central meeting place, few cultural amenities, a need for arts programming, etc. Other liabilities within a neighbourhood may include a vacant lot that attracts illegal activity, abandoned buildings or vehicles that attract rodents or other undesirables. Useful strategies can be implemented for such liabilities like a community garden in place of the vacant lot or an arts habitat created by the abandoned building. It will be the youth's ideas and input that will determine the most viable and worthwhile solutions for their community.

Once the assessment of the communities assets and liabilities is complete, students will have the opportunity to “fix” their neighbourhood within he virtual model they have created. Without any red tape, politics or bureaucracy, students will implement their ideas into their virtual model and transform the land to reflect their visions. Having evoked change within their virtual world, students will now begin work on a public presentation of their work. This presentation will include the findings of the asset-mapping project, the virtual model of the community and finally the vision statement of what these youth see as the most important community building initiatives. This presentation would be open to the public and would encourage all local residents and business people to attend. Local MLA's and city planners would receive personal invitations to the presentation and every effort would be made to involve local government. Ideally this presentation would foster interest within the business community and result in at least some of the strategies developed through OYFD being implemented within the community. Support letters from residents and businesses within the community along with the asset-map and virtual environment that these students create will certainly make an impressive package to write a community grant around. Once the project is complete, students can further demonstrate their engagement through the pursuit of these provincial funds.

Upon completion of all OYFD activities, students will be re-assessed by way of a post test to determine the students knowledge about what community development is, how one gets involved, the assets within their own community, and the level of participation they plan to show in the future. This post test is the final leg of the students involvement in OYFD.